## CMS_ CHINA MED (NEW)
PEAK SHIPPING LINE LIMITED
CHINA MEDITERRANEAN SERVICE (CMS)
|  |  | VSL CODE | OPR | Voy |  |  | NINGBO |  | NANSHA | [9 empty] | Voy | ADEN | [5 empty] | DJIBOUTI |  |  |  | Voy | JEDDAH |  |  | Voy
[8 empty] | CNNGB |  | CNNSA | [10 empty] | YEADE | [5 empty] | DJJIB |  |  |  |  | SAJED
[8 empty] | TBA |  | NICT | [10 empty] | ACT | [5 empty] | SGTD |  |  |  |  | RSGT
[8 empty] | ETA | ETD | ETA | ETD | [7 empty] | ETD |  | ETA | ETD |  |  |  |  | ETA | ETD |  |  |  | ETA |  | ETD
|  | ZHONG PENG YOU YI | DTS | DTS | EXP 24001W |  |  | 2024-08-10 | 2024-08-11 | 2024-08-13 | 2024-08-14 | [7 empty] | #REF! | IMP 24001W EXP 24001N | #REF! | #REF! |  |  |  |  | #REF! | #REF! |  |  | IMP 24001N EXP 24001S | #REF! |  | #REF! | IMP 24001S EXP 24001E
|  | JI ZHE 3 | PKS | PKS | IMP 24003E EXP 24004W |  |  | #REF! | #REF! | #REF! | #REF! | [8 empty] | IMP 24004W EXP 24004E | #REF! | #REF! |  |  |  |  | #REF! | #REF! |  |  |  | #REF!
CYCLE | WEEK | VESSEL NAME | VSL CODE | OPR | Voy | QINGDAO |  | NINGBO |  | NANSHA |  | PORT KELANG | [7 empty] | DJIBOUTI |  | JEDDAH | [5 empty] | Voy |  |  | SOKHNA |  | ADEN | NINGBO
[6 empty] | CNTAO |  | CNNGB |  | CNNSA |  | MYPKG | [7 empty] | DJJIB |  | SAJED | [8 empty] | EGSOK |  | YEADE | CNNGB
[6 empty] | QQCT |  | ZYCT |  | NICT |  | WEST PORT | [7 empty] | SGTD |  | RSGT | [8 empty] | SCT |  | ACT | ZYCT
[6 empty] | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | [5 empty] | ETD | ETA | ETD | ETA |  |  |  |  | ETD |  |  |  | ETA | ETD | ETA | ETA | ETD
| 33 | ZHONG PENG YOU YI | DTS | DTS | EXP 24001W | 2024-08-12 | 2024-08-13 | 2024-08-15 | 2024-08-16 | 2024-08-19 | 2024-08-20 | [7 empty] | #REF! | #REF! | #REF! | #REF! |  |  |  |  | #REF! | IMP 24001W EXP 24001E |  |  | #REF! | #REF! |  | #REF! | #REF!
CYCLE | WEEK | VESSEL NAME | VSL CODE | OPR | VOY | 2024-08-12: QINGDAO; 2024-08-15: SHANGHAI; 2024-08-19: NANSHA | JEDDAH |  |  |  | ALEXANDRIA |  | VOY | ISTANBUL KUMPORT |  | IZMIT |  | ALEXANDRA |  |  |  | JEDDAH |  | PORT KLANG |  | NANSHA |  | QINGDAO
[6 empty] | 2024-08-12: CNTAO; 2024-08-15: CNSHA; 2024-08-19: CNNSA | SAJED |  | EGSUZ |  | EGALY |  |  | TRIST |  | TRIZT |  | EGALY |  | EGSUZ |  | SAJED |  | MYPKG |  | CNNSA |  | CNTAO
[6 empty] | 2024-08-12: QQCT; 2024-08-15: WGQ 5; 2024-08-19: NICT 3 | RSGT |  |  |  | ACCHCo |  |  | MARDAS |  | EVYAP |  | ACCHCo |  |  |  | RSGT |  | WP |  | NICT 3 |  | QQCT
[6 empty] | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD |  | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA
11 | 18 | CUL BANGKOK | TBA | CUL | EXP 2518 W | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-04 | 2025-05-04 | 2025-05-23 | 2025-05-23 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | IMP 2518 W EXP 2518 E | 2025-05-30 | 2025-06-01 | 2025-06-02 | 2025-06-04 | 2025-06-07 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-11 | 2025-06-12 | 2025-06-26 | 2025-06-27 | 2025-07-02 | 2025-07-03 | 2025-07-07 |  | 70 | DAYS
| 19 | CUL HOCHIMINH | TBA | CUL | EXP 2520 W | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-11 | 2025-05-11 | 2025-05-30 | 2025-05-30 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | IMP 2520 W EXP 2520 E | 2025-06-06 | 2025-06-08 | 2025-06-09 | 2025-06-11 | 2025-06-14 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-18 | 2025-06-19 | 2025-07-03 | 2025-07-04 | 2025-07-09 | 2025-07-10 | 2025-07-14 |  | 70 | DAYS
| 20 | MARSA NEPTUNE | TBA | MARSA | EXP 2503 W | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-18 | 2025-05-18 | 2025-06-06 | 2025-06-06 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | IMP 2503 W EXP 250 3E | 2025-06-13 | 2025-06-15 | 2025-06-16 | 2025-06-18 | 2025-06-21 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-25 | 2025-06-26 | 2025-07-10 | 2025-07-11 | 2025-07-16 | 2025-07-17 | 2025-07-21 |  | 70 | DAYS
| 21 | SAFEEN PROSPER | TBA | GFS | EXP 2521W | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-25 | 2025-05-25 | 2025-06-13 | 2025-06-13 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | IMP 2521 W EXP 2521 E | 2025-06-20 | 2025-06-22 | 2025-06-23 | 2025-06-25 | 2025-06-28 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-02 | 2025-07-03 | 2025-07-17 | 2025-07-18 | 2025-07-23 | 2025-07-24 | 2025-07-28 |  | 70 | DAYS
| 22 | CUL SHEKOU | TBA | CUL | EXP 2522 W | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-06-01 | 2025-06-01 | 2025-06-20 | 2025-06-20 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | IMP 2522 W EXP 2522 E | 2025-06-27 | 2025-06-29 | 2025-06-30 | 2025-07-02 | 2025-07-05 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-09 | 2025-07-10 | 2025-07-24 | 2025-07-25 | 2025-07-30 | 2025-07-31 | 2025-08-04 |  | 70 | DAYS
| 23 | CUL SHEKOU | TBA | CUL | EXP 2522 W | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-08 | 2025-06-08 | 2025-06-27 | 2025-06-27 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | IMP 2522 W EXP 2522 E | 2025-07-04 | 2025-07-06 | 2025-07-07 | 2025-07-09 | 2025-07-12 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-16 | 2025-07-17 | 2025-07-31 | 2025-08-01 | 2025-08-06 | 2025-08-07 | 2025-08-11
| 24 | NZ SUZHOU | TBA | MAS | EXP 56 W | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-15 | 2025-06-15 | 2025-07-04 | 2025-07-04 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | IMP 56 W EXP 56 E | 2025-07-11 | 2025-07-13 | 2025-07-14 | 2025-07-16 | 2025-07-19 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-23 | 2025-07-24 | 2025-08-07 | 2025-08-08 | 2025-08-13 | 2025-08-14 | 2025-08-18 |  | 70 | DAYS
| 25 | CUL MANILA | TBA | CUL | EXP 2524 W | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-22 | 2025-06-22 | 2025-07-11 | 2025-07-11 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | IMP 2524 W EXP 2524 E | 2025-07-18 | 2025-07-20 | 2025-07-21 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-30 | 2025-07-31 | 2025-08-14 | 2025-08-15 | 2025-08-20 | 2025-08-21 | 2025-08-25 |  | 70 | DAYS
| 26 | CUL TBN | TBA | CUL | EXP 2525 W | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-29 | 2025-06-29 | 2025-07-18 | 2025-07-18 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | IMP 2525 W EXP 2525 E | 2025-07-25 | 2025-07-27 | 2025-07-28 | 2025-07-30 | 2025-08-02 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-06 | 2025-08-07 | 2025-08-21 | 2025-08-22 | 2025-08-27 | 2025-08-28 | 2025-09-01 |  | 70 | DAYS
| 27 | NZ NINGBO | TBA | MAS | EXP 59 W | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-06 | 2025-07-06 | 2025-07-25 | 2025-07-25 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | IMP 59 W EXP 59 E | 2025-08-01 | 2025-08-03 | 2025-08-04 | 2025-08-06 | 2025-08-09 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-13 | 2025-08-14 | 2025-08-28 | 2025-08-29 | 2025-09-03 | 2025-09-04 | 2025-09-08 |  | 70 | DAYS
| 28 | GFS PRIDE | TBA | GFS | EXP 2527 W | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-06 | 2025-07-06 | 2025-07-25 | 2025-07-25 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | IMP 2527 W EXP 2527 E | 2025-08-01 | 2025-08-03 | 2025-08-04 | 2025-08-06 | 2025-08-09 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-13 | 2025-08-14 | 2025-08-28 | 2025-08-29 | 2025-09-03 | 2025-09-04 | 2025-09-08 |  | 70 | DAYS
* Above LTS subject to changes without Prior Notice
Remarks
Maiden Voyage kicking start W.e.f MV SAFEEN PROSPER 2521 W/E at CNTAO on 19 May 25
Formulas:
ETD = [NINGBO]+1
ETD = [NANSHA]+1
NANSHA = [ETD]+2
PORT KELANG = [ETD]+19
EGSUZ = [ETD]+2
Voy = [ETD]+2
ADEN = [Voy]+1
ADEN = [JEDDAH]+4
ALEXANDRA = [ETD]+3
DJIBOUTI = [ETD]+2
PORT KLANG = [ETD]+14
JEDDAH = [Voy]+1

## SUMMIT YDS (hidden)
Summit Shipping Line Pte,. Ltd
JEA- ADE-JIB SHUTTLE SERVICE
Vessel | VSL CODE | OPR | Voy | ADEN |  | DJIBOUTI |  | Voy | JEBEL ALI |  | Voy | ADEN
|  |  |  | YEADE |  | DJJIB |  |  | AEJEA |  |  | YEADE
|  |  |  | ACT |  | SGTD |  |  | T1 |  |  | ACT
|  |  |  | ETA | ETD | ETA | ETD |  | ETA | ETD |  | ETA | ETD
JI ZHE 2 | SUM | SUM | EXP 24002E | 2024-03-01 | 2024-03-02 | 2024-03-02 | 2024-03-07 | IMP 24002E EXP 24003W | 2024-03-15 | 2024-03-21 | IMP 24003W | 2024-03-29 | 2024-03-30
JI ZHE 2 | SUM | SUM | EXP 24003E | 2024-03-29 | 2024-03-30 | 2024-03-30 | 2024-04-07 | IMP 24003E EXP 24004W | 2024-04-15 | 2024-04-20 | IMP 24004W | 2024-04-28 | 2024-04-29
JI ZHE 2 | SUM | SUM | EXP 24004E | 2024-04-28 | 2024-04-29 | 2024-04-29 | 2024-04-30 | IMP 24004E EXP 24005W | 2024-05-08 | 2024-05-15 | IMP 24005W | 2024-05-22 | 2024-05-23
JI ZHE 2 | SUM | SUM | EXP 24005E | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-24 | IMP 24005E EXP 24006W | 2024-06-01 | 2024-06-03 | IMP 24006W | 2024-06-15 | 2024-06-16
Vessel | VSL CODE | OPR | Voy | DJIBOUTI |  | ADEN |  | Voy | JEBEL ALI |  | Voy | DJIBOUTI
|  |  |  | DJJIB |  | YEADE |  |  | AEJEA |  |  | DJJIB
|  |  |  | SGTD |  | ACT |  |  | T1 |  |  | SGTD
|  |  |  | ETA | ETD | ETA | ETD |  | ETA | ETD |  | ETA | ETD
JI ZHE 2 | SUM | SUM | EXP 24005E | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-24 | IMP 24005E EXP 24006W | 2024-06-01 | 2024-06-03 | IMP 24006W | 2024-06-15 | 2024-06-16
JI ZHE 2 | SUM | SUM | EXP 24006E | 2024-06-14 | 2024-06-15 | 2024-06-15 | 2024-06-16 | IMP 24006E EXP 24007W | 2024-06-24 | 2024-06-28 | IMP 24007W | 2024-07-11 | 2024-07-12
Vessel | VSL CODE | OPR | Voy | DJIBOUTI |  | ADEN |  | Voy | JEBEL ALI |  | Voy | ADEN
|  |  |  | DJJIB |  | YEADE |  |  | AEJEA |  |  | YEADE
|  |  |  | SGTD |  | ACT |  |  | T1 |  |  | ACT
|  |  |  | ETA | ETD | ETA | ETD |  | ETA | ETD |  | ETA | ETD
JI ZHE 2 | SUM | SUM | EXP 24007E | 2024-07-11 | 2024-07-12 | 2024-07-13 | 2024-07-14 | IMP 24007E EXP 24008W | 2024-07-22 | 2024-07-24 | IMP 24008W | 2024-08-07 | 2024-08-10
Vessel | VSL CODE | OPR | Voy | ADEN |  | DJIBOUTI |  | Voy | JEBEL ALI |  | Voy | DJIBOUTI
|  |  |  | YEADE |  | DJJIB |  |  | AEJEA |  |  | DJJIB
|  |  |  | ACT |  | SGTD |  |  | T1 |  |  | SGTD
|  |  |  | ETA | ETD | ETA | ETD |  | ETA | ETD |  | ETA | ETD
JI ZHE 2 | SUM | SUM | EXP 24008E | 2024-08-07 | 2024-08-10 | 2024-08-11 | 2024-08-12 | IMP 24008E EXP 24009W | 2024-08-21 | 2024-08-26 | IMP 24009W | 2024-09-07 | 2024-09-10
Vessel | VSL CODE | OPR | Voy | DJIBOUTI |  | ADEN |  | Voy | JEBEL ALI |  | Voy | ADEN |  | DJIBOUTI
|  |  |  | DJJIB |  | YEADE |  |  | AEJEA |  |  | YEADE |  | DJJIB
|  |  |  | SGTD |  | ACT |  |  | T1 |  |  | ACT |  | SGTD
|  |  |  | ETA | ETD | ETA | ETD |  | ETA | ETD |  | ETA | ETD | ETA | ETD
JI ZHE 2 | SUM | SUM | EXP 24009E | 2024-09-07 | 2024-09-10 | 2024-09-11 | 2024-09-12 | IMP 24009E EXP 24010W | 2024-09-21 | 2024-09-23 | IMP 24010W | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-07 | PHASE-OUT of YDS
Vessel | VSL CODE | OPR | Voy | ADEN |  | DJIBOUTI |  | Voy | JEBEL ALI |  | Voy | ADEN
|  |  |  | YEADE |  | DJJIB |  |  | AEJEA |  |  | YEADE
|  |  |  | ACT |  | SGTD |  |  | T1 |  |  | ACT
|  |  |  | ETA | ETD | ETA | ETD |  | ETA | ETD |  | ETA | ETD
JI ZHE 3 | SUM | SUM | EXP 24003E | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | IMP 24003E EXP 24004W | 2024-08-16 | 2024-08-18 | IMP 24004W | 2024-08-26 | 2024-08-26 | Phase-in from CYE svc
JI ZHE 3 | SUM | SUM | EXP 24004E | 2024-08-26 | 2024-08-26 | 2024-09-23 | 2024-09-24 | IMP 24004E | [5 empty] | Downline Voy TBA
JI ZHE 3 | SUM | SUM | EXP 24005E | 0 | 0 | 1899-12-31 | 1900-01-01 | IMP 24005E EXP 24006W | 1900-01-08 | 1900-01-10 | IMP 24006W | 1900-01-18 | 1900-01-19 | 1900-01-31
JI ZHE 3 | SUM | SUM | EXP 24006E | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | IMP 24006E EXP 24007W | 1900-01-28 | 1900-01-30 | IMP 24006W | 1900-02-07 | 1900-02-08
Remarks
JI ZHE 3 24004 has berth DJJIB on 23th SEP for discharge , downline Voy TBA
JI ZHE 2 will phase out at DJIBOUTI after discharging cargo from Voy 24010W & proceed for Dry Dock.
JI ZHE 3 24004E faced delays at DJJIB call due to recent incident at GPS: 11°41.72N, 043°08.63E. off Djibouti port, due to unexpected strong wind. Downline TBA
JI ZHE 2 24009W faced 3 Days delay due to bad weather & congestion at JEA port .
JI ZHE 2 24008 faced bad delay due to bad weather at sea ETB ADE 7/8 .
JI ZHE 3 24003E Phase -in to YDS svc at ADE on 6/8 to cater overflows
MV JI ZHE 2 24010 Phase-out after completion of WB discharge at YEADE
MV JI ZHE3 24004E Phase-in to replace JIZHE 2 at YEADE.
MV 24007E Delays berth at DJJIB due to bad weather & port congestion. POB 11 Jul PM.
MV 24007E switch call for DJJIB before YEADE, ETA AEJEA remains on 14 Jul.
MV 24006E switch call for DJJIB before YEADE, ETA AEJEA remains on 23 Jun.
MV 24005W 5 Days Delays prior to berth at AEJEA due Port Congestion
MV 24003E 7 Days Delays prior to berth at DJJIB due Port Congestion
MV 24003W 5 Days Delays prior to berth at AEJEA due Port Congestion
MV 24002E was delayed for 3 Days prior to berth at Djibouti due to Port Congestion
Formulas:
ETD = [ADEN]+1
ETD = [DJIBOUTI]+1+4
DJIBOUTI = [ETD]
DJIBOUTI = [ETD]+1
JEBEL ALI = [ETD]+8
JEBEL ALI = [ETD]+8+1
ADEN = [ETD]+8
ADEN = [ADEN, row above]

## SUMMIT CRE (NEW) (hidden)
Summit Shipping Line Pte,. Ltd
CHINA REDSEA EXPRESS (CRE) *NEW
CYCLE | WEEK | VESSEL NAME | VSL CODE | OPR | VOY | QINGDAO |  | NINGBO |  | VOY | SOKHNA |  | JEDDAH |  | QINGDAO
[6 empty] | CNTAO |  | CNNGB |  |  | EGSOK |  | SAJED |  | CNTAO
[6 empty] | QQCT |  | ZYCT |  |  | SCT |  | RSGT |  | QQCT
[6 empty] | ETA | ETD | ETA | ETD |  | ETA | ETD | ETA | ETD | ETA | ETD
1 | 46
47
| 48 | ZHI YING HE SHUN | ZYHS | OSL | EXP 24005W | 2024-11-29 | 2024-11-30 | 2024-12-02 | 2024-12-03 | IMP 24005W EXP 24005E | 2024-12-28 | 2024-12-30 | 2025-01-01 | 2025-01-03 | 2025-01-27 | 2025-01-28 | Target to omit EGSOK
| 49 | HUI FENG HAI |  | OSL | EXP 24002W | 2024-12-06 | 2024-12-07 | 2024-12-09 | 2024-12-10 | IMP 24002W EXP 24002E | 2025-01-04 | 2025-01-06 | 2025-01-08 | 2025-01-10 | 2025-02-03 | 2025-02-04
50
| 51 | HT WEALTH |  | OSL | EXP 24003W | 2024-12-17 | 2024-12-18 | 2024-12-20 | 2024-12-21 | IMP 24003W EXP 24003E | 2025-01-15 | 2025-01-17 | 2025-01-19 | 2025-01-21 | 2025-02-14 | 2025-02-15
| 52 | ZHONG PENG YOU YI | ZPY | SUM | EXP 24003W | 2024-12-24 | 2024-12-25 | 2024-12-27 | 2024-12-28 | IMP 24003W EXP 24003E | 2025-01-22 | 2025-01-24 | 2025-01-26 | 2025-01-28 | 2025-02-21 | 2025-02-22
01
02
2 | 03
| 04 | ZHI YING HE SHUN | ZYHS | OSL | EXP 24006W | 2025-01-20 | 2025-01-21 | 2025-01-23 | 2025-01-24 | IMP 24006W EXP 24006E | 2025-02-18 | 2025-02-20 | 2025-02-22 | 2025-02-24 | 2025-03-20 | 2025-03-21
| 05 | HUI FENG HAI |  | OSL | EXP 24003W | 2025-01-27 | 2025-01-28 | 2025-01-30 | 2025-01-31 | IMP 24003W EXP 24003E | 2025-02-25 | 2025-02-27 | 2025-03-01 | 2025-03-03 | 2025-03-27 | 2025-03-28 | Target ETA CNTAO 21/1 | at 11.5 knots
| 06 | [15 empty] | Target ETA CNTAO 27/1 | at 12.5 knots
| 07 | HT WEALTH |  | OSL | EXP 24004W | 2025-02-14 | 2025-02-15 | 2025-02-17 | 2025-02-18 | IMP 24004W EXP 24004E | 2025-03-15 | 2025-03-17 | 2025-03-19 | 2025-03-21 | 2025-04-14 | 2025-04-15
| 08 | ZHONG PENG YOU YI | ZPY | SUM | EXP 24004W | 2025-02-21 | 2025-02-22 | 2025-02-24 | 2025-02-25 | IMP 24004W EXP 24004E | 2025-03-22 | 2025-03-24 | 2025-03-26 | 2025-03-28 | 2025-04-21 | 2025-04-22
09
10
| 11 | -
Formulas:
ETD = [QINGDAO]+1
ETD = [NINGBO]+1
NINGBO = [ETD]+2

## SUMMIT CRE (hidden)
Summit Shipping Line Pte,. Ltd
CHINA REDSEA EXPRESS (CRE)
|  |  | VSL CODE | OPR | Voy |  |  | NINGBO |  | NANSHA |  |  |  | PORT KLANG |  | Voy | ADEN |  | DJIBOUTI |  |  |  | Voy | JEDDAH |  |  |  | SOKHNA |  | Voy
[8 empty] | CNNGB |  | CNNSA |  |  |  | MYPKG |  |  | YEADE |  | DJJIB |  |  |  |  | SAJED |  |  |  | EGSOK
[8 empty] | TBA |  | NICT |  |  |  | WEST PORT |  |  | ACT |  | SGTD |  |  |  |  | RSGT |  |  |  | DPW
[8 empty] | ETA | ETD | ETA | ETD |  |  | ETA | ETD |  | ETA | ETD | ETA | ETD |  |  |  | ETA |  |  | ETD | ETA | ETD
|  | ZHONG PENG YOU YI | DTS | DTS | EXP 24001W |  |  | 2024-08-10 | 2024-08-11 | 2024-08-13 | 2024-08-14 |  |  | 2024-08-19 | 2024-08-20 | IMP 24001W EXP 24001N | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 |  |  | IMP 24001N EXP 24001S | 2024-09-06 |  |  | 2024-09-07 | 2024-09-09 | 2024-09-10 | IMP 24001S EXP 24001E
|  | JI ZHE 3 | PKS | PKS | IMP 24003E EXP 24004W |  |  | 2024-09-06 | 2024-09-07 | 2024-09-10 | 2024-09-11 |  |  |  |  | IMP 24004W EXP 24004E | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 |  |  |  | 2024-10-26 |  |  | 2024-10-27
CYCLE | WEEK | VESSEL NAME | VSL CODE | OPR | Voy | QINGDAO |  | NINGBO |  | NANSHA |  | PORT KELANG |  | ADEN |  | DJIBOUTI |  | JEDDAH |  | Voy |  |  | SOKHNA |  | ADEN |  | QINGDAO |  | NINGBO
[6 empty] | CNTAO |  | CNNGB |  | CNNSA |  | MYPKG |  | YEADE |  | DJJIB |  | SAJED |  |  |  |  | EGSOK |  | YEADE |  | CNTAO |  | CNNGB
[6 empty] | QQCT |  | ZYCT |  | NICT |  | WEST PORT |  | ACT |  | SGTD |  | RSGT |  |  |  |  | SCT |  | ACT |  | QQCT |  | ZYCT
[6 empty] | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD |  |  |  | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD
| 33 | ZHONG PENG YOU YI | DTS | DTS | EXP 24001W | 2024-08-12 | 2024-08-13 | 2024-08-15 | 2024-08-16 | 2024-08-19 | 2024-08-20 |  |  | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-15 | 2024-09-16 | 2024-09-17 | IMP 24001W EXP 24001E |  |  | 2024-09-20 | 2024-09-21 |  |  |  |  | 2024-10-16 | 2024-10-17
CYCLE | WEEK | VESSEL NAME | VSL CODE | OPR | VOY | 2024-08-12: NINGBO; 2024-08-15: XIAMEN; 2024-08-19: NANSHA |  |  | VOY | JEDDAH |  | SOKHNA |  | AQABA |  | ADEN |  | JEBEL ALI |  | PORT KELANG |  | NINGBO
[6 empty] | 2024-08-12: CNNGB; 2024-08-15: CNXMN; 2024-08-19: CNNSA |  |  |  | SAJED |  | EGSOK |  | JOAQJ |  | YEADE |  | AEJEA |  | MYPKG |  | CNNGB
[6 empty] | 2024-08-12: ZYCT; 2024-08-15: XIC; 2024-08-19: NICT |  |  |  | RSGT |  | SCT |  | ACT |  | ACT |  | TBA |  | WP |  | ZYCT
[6 empty] | ETA | ETD | ETA | ETD | ETA | ETD |  |  |  | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD
1 | 37 | - | BLK1 | - | -
| 38 | CHANG SHUN JIN XIU | CSX | SLC | EXP 2410W | 2024-09-27 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 | 2024-10-07 |  |  | IMP 2410W EXP 2410E | 2024-10-26 | 2024-10-27 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-10-31 |  |  |  |  | 2024-11-19 | 2024-11-21 | 2024-11-28 | 2024-11-28
| 39 | ASL HONG KONG | EHK | ESL | EXP 02439W | 2024-09-28 | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-06 |  |  | IMP 02439W EXP 02439E | 2024-10-24 | 2024-10-24 | 2024-10-26 | 2024-10-27 | 2024-10-28 | 2024-10-28 |  |  | 2024-11-07 | 2024-11-08
| 40 | - | BLK2 | - | -
| 41 | XIN YONG CHANG 19 | XYC | SLC | EXP 2420W | 2024-10-14 | 2024-10-16 | 2024-10-18 | 2024-10-18 | 2024-10-19 | 2024-10-20 |  |  | IMP 2420W EXP 2420E | 2024-11-10 | 2024-11-11 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | [6 empty] | 2024-12-08 | 2024-12-09
| 42 | ZHONG PENG YOU YI | ZPY | SUM | EXP 24002W | 2024-10-19 | 2024-10-20 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-24 |  |  | IMP 24002W EXP 24002E | 2024-11-17 | 2024-11-19 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-30 | 2024-12-01 |  |  | 2024-12-12 | 2024-12-13 | 2024-12-22 | 2024-12-25
| 43 | - | BLK3 | - | -
| 44 | - | BLK4 | - | -
2 | 45 | A Daisen | TBA | SLC | EXP TBA | 2024-11-10 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 |  |  | IMP TBA EXP TBA | 2024-12-01 | 2024-12-02 | 2024-12-04 | 2024-12-05 | 2024-12-07 | 2024-12-08 |  |  | 2024-12-25 | 2024-12-26 |  |  | 2025-01-04 | 2025-01-05
| 46 | - | BLK1 | - | -
| 47 | ASL HONG KONG | EHK | ESL | EXP 02440W | -1 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 |  |  | IMP 02440W EXP 02440E | 1900-01-22 | 1900-01-23 | 1900-01-25 | 1900-01-26 | 1900-01-28 | 1900-01-29 |  |  | 1900-02-15 | 1900-02-16 |  |  | 1900-02-25 | 1900-02-26
| 48 | - | BLK2 | - | -
| 49 | XIN YONG CHANG 19 | XYC | SLC | EXP 2421W | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 |  |  | IMP 2421W EXP 2421E | 2024-12-31 | 2025-01-01 | 2025-01-03 | 2025-01-04 | 2025-01-06 | 2025-01-07 |  |  | 2025-01-24 | 2025-01-25 |  |  | 2025-02-03 | 2025-02-04
| 50 | - | BLK3 | - | -
| 51 | ZHONG PENG YOU YI | ZPY | SUM | EXP 24003W | 2024-12-29 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 |  |  | IMP 24003W EXP 24003E | 2025-01-20 | 2025-01-21 | 2025-01-23 | 2025-01-24 | 2025-01-26 | 2025-01-27 |  |  | 2025-02-13 | 2025-02-14 |  |  | 2025-02-23 | 2025-02-24
| 52 | - | BLK4 | - | -
Remarks
MV ZHONG PENG YOU YI will add YEADE as private call after JOAQJ .
MV XIN YONG CHANG 19 will omit MYPKG & Call CNNGB Direct .
MV ASL HONG KONG 02439 will omit MYPKG & Phase-Out at AEJEA. VO will provide connection for MYPKG & CNNGB via AEJEA
MV CHANG SHUN JIN XIU 2401W delayed from proforma due to bad weather at sea & port congestion at CNNGB.
CRE_ Consortium Service kick start wef MV CHANG SHUN JIN XIU 2410W at CNNGB on WK 38 , with New Rotaion / Proforma LTS
MV Zhong Peng You Yi 24001E is omitting CNTAO & will call direct to CNNGB & Phase-In to Consortium Service on wk42
MV 24001W delay in calling YEADE, due to bad weather & rough sea condition. Downline calls adjusted accordingly.
MV 24001W will be omitting DJJIB , affected cargos onbaord will be discharge & T/S in YEADE to connect 2nd carrier on wk37/38 for DJJIB
(NEW SVC) Maiden Voyage EX CHINA_ 1st Port _CNTAO 10-12 Aug
Formulas:
ETD = [NINGBO]+1
ETD = [NANSHA]+1
NANSHA = [ETD]+2
PORT KLANG = [ETD]+5
PORT KLANG = [ETD]+18+5
ADEN = [ETD]+12
ADEN = [Voy]+1
JEDDAH = [ETD]+2
JEDDAH = [Voy]+1
SOKHNA = [ETD]+2
SOKHNA = [ETD]
NINGBO = [JEDDAH, row above]
NINGBO = [ETD]+2
Voy = [ETD]+1
Voy = [DJIBOUTI]+3
DJIBOUTI = [ETD]+1

## SUMMIT CYE (hidden)
Summit Shipping Line Pte,. Ltd
CHINA YEMEN EXPRESS (CYE)
Vessel | VSL CODE | OPR | Voy | NINGBO |  | NANSHA |  | PORT KLANG |  | Voy | JEBEL ALI |  | Voy | ADEN |  | NINGBO
|  |  |  | CNNGB |  | CNNSA |  | MYPKG |  |  | AEJEA |  |  | YEADE |  | CNNGB
|  |  |  | NBCT |  | NICT |  | WEST PORT |  |  | T1 |  |  | ACT |  | NBCT
|  |  |  | ETA | ETD | ETA | ETD | ETA | ETD |  | ETA | ETD |  | ETA | ETD | ETA | ETD
JI ZHE 3 | SUM | SUM | EXP 24002W | 2024-04-24 | 2024-04-25 | 2024-04-28 | 2024-04-30 | 2024-05-07 | 2024-05-08 | EXP 24002W | 2024-05-20 | 2024-05-29 | IMP 24002W EXP 24002E | 2024-06-05 | 2024-06-07 | 2024-07-02 | 2024-07-03
Vessel | VSL CODE | OPR | Voy | 2024-04-24: NINGBO; 2024-04-28: SHEKOU; 2024-05-07: PORT KLANG | Voy | ADEN |  | DJIBOUTI
|  |  |  | 2024-04-24: CNNGB; 2024-04-28: CNSHK; 2024-05-07: MYPKG |  | YEADE |  | DJJIB
|  |  |  | 2024-04-24: NBCT; 2024-05-07: WEST PORT |  | ACT |  | SGTD
|  |  |  | ETA | ETD | ETA | ETD | ETA | ETD |  | ETA | ETD | ETA | ETD
JI ZHE 3 | SUM | SUM | EXP 24003W | 2024-07-02 | 2024-07-03 | 2024-07-07 | 2024-07-08 | 2024-07-16 | 2024-07-16 | IMP 24003W | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | Phase In to YDS
Vessel | VSL CODE | OPR | Voy | ADEN |  | DJIBOUTI |  | Voy | JEBEL ALI |  | Voy | ADEN |  | DJIBOUTI
|  |  |  | 2024-04-24: YEADE; 2024-04-28: DJJIB; 2024-05-08: AEJEA |  |  | YEADE |  | DJJIB
|  |  |  | 2024-04-24: ACT; 2024-04-28: SGTD; 2024-05-08: T1 |  |  | ACT |  | SGTD
|  |  |  | ETA | ETD | ETA | ETD |  | ETA | ETD |  | ETA | ETD | ETA | ETD
JI ZHE 3 | SUM | SUM | EXP 24003E | 2024-08-07 | 2024-08-08 | 2024-08-09 | 2024-08-10 | IMP 24003E EXP 24004W | 2024-08-17 | 2024-08-18 | IMP 24004W EXP 24004E | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29
==OPTION==
Vessel | VSL CODE | OPR | Voy | ADEN |  | DJIBOUTI |  | Voy | MUNDRA |  | ADEN |  | DJIBOUTI
|  |  |  | 2024-04-24: YEADE; 2024-04-28: DJJIB; 2024-05-08: INMUN |  | YEADE |  | DJJIB
|  |  |  | 2024-04-24: ACT; 2024-04-28: SGTD; 2024-05-08: TBA |  | ACT |  | SGTD
|  |  |  | ETA | ETD | ETA | ETD |  | ETA | ETD | ETA | ETD | ETA | ETD
JI ZHE 3 | SUM | SUM | EXP 24004E | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | IMP 24004E EXP 24005W | 2024-09-12 | 2024-09-13 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-26 | Phase In to YDS
Vessel | VSL CODE | OPR | Voy | ADEN |  | DJIBOUTI |  | Voy | 2024-09-12: SOKHNA; 2024-09-23: DJIBOUTI; 2024-09-25: ADEN
|  |  |  | YEADE |  | DJJIB |  |  | 2024-09-12: EGSOK; 2024-09-23: DJJIB; 2024-09-25: YEADE
|  |  |  | ACT |  | SGTD |  |  | 2024-09-12: TBA; 2024-09-23: SGTD; 2024-09-25: ACT
|  |  |  | ETA | ETD | ETA | ETD |  | ETA | ETD | ETA | ETD | ETA | ETD
JI ZHE 3 | SUM | SUM | EXP 24004N | 2024-08-26 | 2024-08-27 | 2024-08-28 | 2024-08-29 | IMP 24004N EXP 24004S | 2024-09-06 | 2024-09-07 | 2024-09-15 | 2024-09-16 | 2024-09-17 | 2024-09-18
Vessel | VSL CODE | OPR | Voy | ADEN |  | DJIBOUTI |  | NINGBO | bar: 2024-09-06
|  |  |  | YEADE |  | DJJIB |  | CNNGB | bar: 2024-09-06
|  |  |  | ACT |  | SGTD |  | YZCT | bar: 2024-09-06
|  |  |  | ETA | ETD | ETA | ETD | ETA | 2024-09-06: ETD
JI ZHE 2 | SUM | SUM | EXP 24010E | 2024-10-03 | 2024-10-04 | 2024-10-05 | 2024-10-07 | 2024-10-31 | 2024-09-06: -; 2024-09-07: Phase out for Drydock.
Remarks
MV JI ZHE 2 Phase-in to CYE service at YEADE & DJJIB on Voy 24010E for CNNGB before proceeding for Drydock.
MV JI ZHE 3 24004W phase-out of CYE & phase-in to YDS svc for EB loading.
MV JI ZHE 2 will replace JI ZHE 3 for EB caller at YEADE on 24010E for CNNGB discharge prior to her Dry-dock.
MV 24003W Calling China Aden & Jibouti direct .
MV 24002W 7 Days Delays prior to berth at AEJEA due Port Congestion
Formulas:
JEBEL ALI = [ETD]+12
ETD = [JEBEL ALI]+2+7
ETD = [ADEN]+2
ADEN = [ETD]+7
ADEN = [Voy]+1
NINGBO = [ETD]+25
Voy = [ETD]+1
NANSHA = [ETD]+1
PORT KLANG = [ETD]+24

## ADHOC_SDR (hidden)
Summit Shipping Line Pte,. Ltd
JEDDAH - DJIBOUTI - ADEN - NINGBO (ADHOC)
Vessel | VSL CODE | OPR | Voy | ADEN |  | DJIBOUTI |  | JEBEL ALI |  | ADEN
|  |  |  | YEADE |  | DJJIB |  | AEJEA |  | YEADE
|  |  |  | ACT |  | SGTD |  | T1 |  | ACT
|  |  |  | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD
JI ZHE 2 | SUM | SUM | EXP 24002E | 2024-03-01 | 2024-03-02 | 2024-03-02 | 2024-03-07 | 2024-03-15 | 2024-03-21 | 2024-03-29 | 2024-03-30
JI ZHE 2 | SUM | SUM | EXP 24003E | 2024-03-29 | 2024-03-30 | 2024-03-30 | 2024-04-07 | 2024-04-15 | 2024-04-20 | 2024-04-28 | 2024-04-29
JI ZHE 2 | SUM | SUM | EXP 24004E | 2024-04-28 | 2024-04-29 | 2024-04-29 | 2024-04-30 | 2024-05-08 | 2024-05-15 | 2024-05-22 | 2024-05-23
JI ZHE 2 | SUM | SUM | EXP 24005E | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-24 | 2024-06-01 | 2024-06-03 | 2024-06-15 | 2024-06-16
Vessel | VSL CODE | OPR | Voy | JEDDAH |  | DJJIBOUTI |  | ADEN |  | NANSHA
|  |  |  | SAJED |  | DJJIB |  | YEADE |  | CNNSA
|  |  |  | RSGT |  | SGTD |  | ACT
|  |  |  | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD
JI ZHE 2 | SUM | SUM | EXP 24005E | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-24 | 2024-06-01 | 2024-06-03 | 2024-06-15 | 2024-06-16
SIDRA AHLAM | SDR | SUM | EXP TRS2406 | 2024-07-31 | 2024-08-01 | 2024-08-03 | 2024-08-04 | 2024-08-06 | 2024-08-09 | 2024-08-30 | -
Remarks
Last Min COD to NANSHA
Adhoc caller EX REDSEA For NINGBO
Formulas:
ETD = [ADEN]+1
ETD = [DJIBOUTI]+1+4
DJIBOUTI = [ETD]
DJIBOUTI = [ETD]+1
JEBEL ALI = [ETD]+8
ADEN = [ETD]+8
ADEN = [ADEN, row above]

## DTS CRE (old) (hidden)
Summit Shipping Line Pte,. Ltd
CHINA REDSEA EXPRESS (CRE)
| VSL CODE | OPR | Voy |  |  | NINGBO |  | NANSHA |  |  |  | PORT KLANG |  | Voy | ADEN |  | DJIBOUTI |  | Voy | JEDDAH |  |  |  | SOKHNA |  | Voy | ADEN |  | NINGBO
[6 empty] | CNNGB |  | CNNSA |  |  |  | MYPKG |  |  | YEADE |  | DJJIB |  |  | SAJED |  |  |  | EGSOK |  |  | YEADE |  | CNNGB
[6 empty] | TBA |  | NICT |  |  |  | WEST PORT |  |  | ACT |  | SGTD |  |  | RSGT |  |  |  | DPW |  |  | ACT
[6 empty] | ETA | ETD | ETA | ETD |  |  | ETA | ETD |  | ETA | ETD | ETA | ETD |  | ETA |  |  | ETD | ETA | ETD |  | ETA | ETD | ETA | ETD
ZHONG PENG YOU YI | DTS | DTS | EXP 24001W |  |  | 2024-08-10 | 2024-08-11 | 2024-08-13 | 2024-08-14 |  |  | 2024-08-19 | 2024-08-20 | IMP 24001W EXP 24001N | 2024-09-01 | 2024-09-02 | 2024-09-03 | 2024-09-04 | IMP 24001N EXP 24001S | 2024-09-06 |  |  | 2024-09-07 | 2024-09-09 | 2024-09-10 | IMP 24001S EXP 24001E | 2024-09-14 | 2024-09-15 | 2024-10-05 | 2024-10-06
JI ZHE 3 | PKS | PKS | IMP 24003E EXP 24004W |  |  | 2024-09-06 | 2024-09-07 | 2024-09-10 | 2024-09-11 |  |  |  |  | IMP 24004W EXP 24004E | 2024-10-02 | 2024-10-03 | 2024-10-04 | 2024-10-05 |  | 2024-10-26 |  |  | 2024-10-27
VESSEL NAME | VSL CODE | OPR | Voy | QINGDAO |  | NINGBO |  | NANSHA |  | PORT KELANG |  | ADEN |  | DJIBOUTI |  | JEDDAH |  | Voy | SOKHNA |  | ADEN |  | QINGDAO |  | NINGBO
|  |  |  | CNTAO |  | CNNGB |  | CNNSA |  | MYPKG |  | YEADE |  | DJJIB |  | SAJED |  |  | EGSOK |  | YEADE |  | CNTAO |  | CNNGB
|  |  |  | TBA |  | TBA |  | NICT |  | WEST PORT |  | ACT |  | SGTD |  | TBA |  |  | TBA |  | ACT |  | TBA |  | TBA
|  |  |  | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD |  | ETA | ETD | ETA | ETD | ETA | ETD | ETA | ETD
ZHONG PENG YOU YI | DTS | DTS | EXP 24001W | 2024-08-10 | 2024-08-10 | 2024-08-12 | 2024-08-13 | 2024-08-16 | 2024-08-16 |  |  | 2024-09-05 | 2024-09-06 | 2024-09-07 | 2024-09-08 | 2024-09-11 | 2024-09-12 | IMP 24001W EXP 24001E | 2024-09-14 | 2024-09-15 |  |  | 2024-10-11 | 2024-10-12 | 2024-10-14 | 2024-10-15
TBA | [5 empty] | 2024-08-30 | 2024-08-31 | 2024-09-03 | 2024-09-03 | 2024-09-10 | 2024-09-11 | 2024-09-23 | 2024-09-24 | 2024-09-25 | 2024-09-27 | 2024-09-30 | 2024-10-01 |  |  |  | 2024-10-04 | 2024-10-05 |  |  | 2024-10-25 | 2024-10-26
ZHONG PENG YOU YI | DTS | DTS | EXP 24002W | 2024-10-11 | 2024-10-12 | 2024-10-14 | 2024-10-15 | 2024-10-18 | 2024-10-18 |  |  | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-13 | 2024-11-14 | IMP 24002W EXP 24002E | 2024-11-16 | 2024-11-17 |  |  | 2024-12-13 | 2024-12-14 | 2024-12-16 | 2024-12-17
TBA | [5 empty] | 2024-10-25 | 2024-10-26 | 2024-10-29 | 2024-10-29 | 2024-11-05 | 2024-11-06 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-22 | 2024-11-25 | 2024-11-26 |  |  |  | 2024-11-29 | 2024-11-30 |  |  | 2024-12-20 | 2024-12-21
ZHONG PENG YOU YI | DTS | DTS | EXP 24003W | 2024-12-13 | 2024-12-14 | 2024-12-16 | 2024-12-17 | 2024-12-20 | 2024-12-20 |  |  | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-15 | 2025-01-16 | IMP 24003W EXP 24003E | 2025-01-18 | 2025-01-19 |  |  | 2025-02-14 | 2025-02-15 | 2025-02-17 | 2025-02-18
TBA | [5 empty] | 2024-12-20 | 2024-12-21 | 2024-12-24 | 2024-12-24 | 2024-12-31 | 2025-01-01 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-17 | 2025-01-20 | 2025-01-21 |  |  |  | 2025-01-24 | 2025-01-25 |  |  | 2025-02-14 | 2025-02-15
ZHONG PENG YOU YI | DTS | DTS | EXP 24004W | 2025-02-14 | 2025-02-15 | 2025-02-17 | 2025-02-18 | 2025-02-21 | 2025-02-21 |  |  | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-19 | 2025-03-20 | IMP 24004W EXP 24004E | 2025-03-22 | 2025-03-23 |  |  | 2025-04-18 | 2025-04-19 | 2025-04-21 | 2025-04-22
TBA | [5 empty] | 2025-02-14 | 2025-02-15 | 2025-02-18 | 2025-02-18 | 2025-02-25 | 2025-02-26 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-14 | 2025-03-17 | 2025-03-18 |  |  |  | 2025-03-21 | 2025-03-22 |  |  | 2025-04-11 | 2025-04-12
Formulas:
ETD = [NINGBO]+1
ETD = [NANSHA]+1
NANSHA = [ETD]+2
PORT KLANG = [ETD]+5
ADEN = [ETD]+12
ADEN = [SOKHNA]+5
DJIBOUTI = [ETD]+1
JEDDAH = [ETD]+2
JEDDAH = [Voy]+1
SOKHNA = [ETD]+2
NINGBO = [ETD]+20
NINGBO = [JEDDAH, row above]
Voy = [ETD]+1
Voy = [DJIBOUTI]+2
PORT KELANG = [ETD]+7